## Sheet1
Gantt chart of Project: Anti-Corruption Reporting System
Project Name: |  | Anti-Corruption Reporting System |  |  | Today's Date: | 19/05/2026
Start Date: |  | 2026-02-05
■ COMPLETED |  | ■ IN PROGRESS |  | ■ PENDING |  | ■ ★ New Feature
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Done | Working Days | Days Done | Days Left
1 | Phase 1: UI Design (HTML/CSS/JS) | Design (HTML/CSS/JS | 2026-05-02 | 28/02/26 | 24 | 100% | 24 | 24 | 0
1.1 | Citizen portal landing page & navigation |  | 2026-05-02 | 2026-10-02 | 6 | 100% | 6 | 6 | 0
1.2 | Complaint submission form layout |  | 2026-11-02 | 16/02/26 | 6 | 100% | 6 | 6 | 0
1.3 | Official / Investigator dashboard |  | 17/02/26 | 22/02/26 | 6 | 100% | 6 | 6 | 0
1.4 | Complaint tracking status & timeline tracker |  | 23/02/26 | 28/02/26 | 6 | 100% | 6 | 6 | 0
2 | Phase 2: Laravel Integration | Core PHP Architecture | 2026-01-03 | 15/3/26 | 15 | 100% | 15 | 15 | 0
2.1 | PHP environment configuration |  | 2026-01-03 | 2026-04-03 | 4 | 100% | 4 | 4 | 0
2.2 | Modular PHP include Layouts |  | 2026-05-03 | 2026-08-03 | 4 | 100% | 4 | 4 | 0
2.3 | Dynamic request routing |  | 2026-09-03 | 2026-11-03 | 3 | 100% | 3 | 3 | 0
2.4 | Tracking ID generation controller |  | 2026-12-03 | 13/03/26 | 2 | 100% | 2 | 2 | 0
2.5 | Role-based session handler |  | 14/03/26 | 15/3/26 | 2 | 100% | 2 | 2 | 0
3 | Phase 3: Database Creation | Dtabase Creation & Modeling | 16/3/26 | 28/03/26 | 13 | 100% | 13 | 13 | 0
3.1 | Design Relational Schema |  | 16/3/26 | 18/03/26 | 3 | 100% | 3 | 3 | 0
3.2 | DB creation via phpMyAdmin |  | 19/03/26 | 22/03/26 | 4 | 100% | 4 | 4 | 0
3.3 | Establishing key constraints & cascading action |  | 23/03/26 | 25/03/26 | 3 | 100% | 3 | 3 | 0
3.4 | Database integrity testing & validation |  | 26/03/26 | 28/03/26 | 3 | 100% | 3 | 3 | 0
4 | Phase 4: PHP: Frontend ↔ Database |  | 28/03/26 | 2026-09-04 | 13 | 100% | 13 | 13 | 0
4.1 | PHP CRUD – submitting complaints |  | 28/03/26 | 31/03/26 | 4 | 100% | 4 | 4 | 0
4.2 | PHP CRUD – Updating investigation statuses |  | 2026-01-04 | 2026-03-04 | 3 | 100% | 3 | 3 | 0
4.3 | Connect frontend forms to target directories |  | 2026-04-04 | 2026-06-04 | 3 | 100% | 3 | 3 | 0
4.4 | Dynamic DB-driven statistics generation |  | 2026-07-04 | 2026-09-04 | 3 | 100% | 3 | 3 | 0
5 | Phase 5: Matching Engine ★ | Secure Document Handling ★ | 2026-10-04 | 24/04/26 | 15 | 0% | 15 | 15 | 15
5.1 | Secure upload handler & backend validation |  | 2026-10-04 | 13/04/26 | 4 | 100% | 4 | 4 | 4
5.2 | Rating & feedback indicators |  | 14/04/26 | 17/04/26 | 4 | 100% | 4 | 4 | 4
5.3 | Automated cryptographic engine for files |  | 18/04/26 | 21/04/26 | 4 | 100% | 4 | 4 | 4
5.4 | Evidence access control checks |  | 22/04/26 | 24/04/26 | 3 | 100% | 3 | 3 | 3
6 | Phase 6: Testing & Debugging | Testing, Audit & Debugging | 25/04/26 | 15/05/26 | 21 | 100% | 21 | 0 | 21
6.1 | Functional validation testing |  | 25/04/26 | 29/05/26 | 5 | 100% | 5 | 5 | 5
6.2 | Security audit & SQL Injection patching |  | 30/04/26 | 2026-04-05 | 5 | 100% | 5 | 5 | 5
6.3 | Performance & load testing |  | 2026-05-05 | 2026-09-05 | 5 | 100% | 5 | 5 | 5
6.4 | Final observation & optimization |  | 2026-10-05 | 15/05/26 | 6 | 100% | 6 | 6 | 6